## Sheet1
Index | Event | Status | Responsible Party | Dependence | Notes
1 | Antenna Radiation Pattern Simulation |  | Osi Van Dessel, Zach Vickerson
2 | Sensor Node Integrity Test |  | Zach Vickerson |  | See Sensor Node Integrity Test Procedure
3 | Develop Test code for in Lab Test |  | Zach Vickerson, Maria Kromis
4 | In Lab Test |  | Zach Vickerson | 2,3 | See In Lab Test Procedure
5 | Modify Test Code for Close Ranged Test |  | Zach Vickerson, Maria Kromis | 2
6 | Integrate Satellite Structure with WSN and Mule boards |  | Zach Vickerson, Paul | 2,4
7 | Close Ranged Test |  | Zach Vickerson, Osi Van Dessel | 4,5 | See Close Ranged Test Procedure
8 | Develop Test Code for Long Range Test |  | Zach Vickerson, Maria Kromis
9 | Procure Materials for Long Range Test |  | Zach Vickerson, Cody Nabong
10 | Long Range Test |  | Zach Vickerson, Cody Nabong, Osi Van Dessell, Maria Kromis | 7,8,9 | See Long Range Test procedure
11 | Develop Test Code for Mesh Network Test |  | Zach Vickerson, Maria Kromis | 5
12 | Mesh Network Test |  | Zach Vickerson, Osi Van Dessel | 11 | See Mesh Network Test Procedure
13 | Develop Test code for Mule Globalstar Test |  | Zach Vickerson, Maria Kromis
14 | Mule GlobalStar Test |  | Zach Vickerson, Osi Van Dessel | 10,13 | See Mule GlobalStar Test Procedure

## Sheet2
Index | Event | Status | Responsible Party | Dependence | Time Table | Notes
1 | Antenna Radiation Pattern Simulation |  | Osi Van Dessel, Zach Vickerson |  | Early February | Initial pattern simulated. May need updating after solar panel design changes
2 | In lab Test |  | Zach Vickerson |  | Early February | See in lab test Procedure. Currently determining status of WSN's. At least 2 working boards are necessary to begin simulated comms testing. New boards are in development, but in the mean time efforts are being made to troubleshoot the various problems with our old boards.
2.a | WSN 1 |  | Zach Vickerson, Osi Van Dessel | 2 | Early February | Faulty Board. Troubleshooting in progress
2.b | WSN 2 |  | Zach Vickerson, Osi Van Dessel | 2 | 2015-11-20 | Board functions!
2.c | WSN 3 |  | Zach Vickerson, Osi Van Dessel | 2 | Early February | Board has broken traces
2.d | WSN 4 |  | Zach Vickerson, Osi Van Dessel | 2 | Early February | Board was troubleshooted over break. Seems to be functional!
2.e | WSN 5 |  | Zach Vickerson, Osi Van Dessel | 2 | Early February | Board shorted out.
3 | Develop Test code for in Lab Test |  | Zach Vickerson, Maria Kromis |  | 2015-10-01 | Code is written. Timing has been tweaked to ensure that both reciever and transmitter switch modulations at the right time.
3.a | Troubleshoot Test code for in Lab test |  | Zach Vickerson | 3,2 | Early February | Timing may still need some tweaking. 2 working boards are necessary to determine any problems.
4 | Procure Materials for Long Range Test |  | Zach Vickerson, Cody Nabong | 4 | Early February | Materials will be procured once in lab test is completed successfully
5 | Develop Code for Close Ranged Test |  | Zach Vickerson, Maria Kromis | 2 | 2015-10-10 | This code is simply an iteration of the in lab test code that stores data on SD card. Initial code is written.
5.a | Modify code for close ranged test |  | Zach Vickerson | 5,3 | Early February | If in lab test timing is modified, close ranged test timing will reflect these changes
6 | Integrate Satellite Structure with WSN and Mule boards |  | Zach Vickerson, Paul | 2,4 | Mid February
7 | Close Ranged Test |  | Zach Vickerson, Osi Van Dessel | 4,5 | Mid February | See Close Ranged Test Procedure
8 | Analyze results of close ranged test |  | Zach Vickerson, Maria Kromis, Osi Van Dessel | 7 | Mid February | Determine ideal data rate and modulation based on test results
9 | Develop Test Code for Long Range Test |  | Zach Vickerson, Maria Kromis | 9 | Mid February | Initial test code has been developed. However this code will be modified to reflect results of close ranged test. This test is also being modified to include the mesh network long range test
10 | Develop Test Code for Mesh Network Test |  | Zach Vickerson, Maria Kromis | 9 | Mid February | Initial code has been developed. Will be modified to reflect results of close ranged test
11 | Mesh Network Close Ranged Test |  | Zach Vickerson, Osi Van Dessel | 11 | Mid Febrary | See Mesh Network Close ranged Test Procedure
12 | Long Range Test |  | Zach Vickerson, Cody Nabong, Osi Van Dessell, Maria Kromis | 4,9,10 | Weather permitting. March | See Long Range Test procedure. The procedure is currently being modified to incorporate the mesh network longrange test.
13 | Develop Test code for Mule Globalstar Test |  | Zach Vickerson, Maria Kromis | 4 | Mid February | Recently procured a radio. Test code is in development. This test could be performed as soon as the wsn's are in good working order. (i.e. succesful in lab test)
14 | Mule GlobalStar Test |  | Zach Vickerson, Osi Van Dessel | 14 | mid February | See Mule GlobalStar Test Procedure
Note: All times are estimates. Testing can be performed rapidly once troubleshooting on the WSN's is completed with the exception of the long range test which will require a day trip to the testing site