## DayInTheLife
Day In The Life: Mule
Power
EPS communication Protocol Development | 2 Weeks | 50%
EPS communication Test | 1 day | 0% | 3
EPS command list test | 3 days | 0% | 4 | power up, power down, read voltage
hardware initialization test | 2 days | 0% | 5 | hardware assembly required
low power mode hardware shutdown design | 3 days | 25%
low power mode power down test | 2 days | 0% | 7 | hardware assembly required
Define additional EPS health information | 1 day | 0%
EPS initialization algorithm | 2 days | 0%
EPS loop flowchart implementation | 3 days | 25% |  | define global variables
low power mode entrance/exit protocol | 3 days | 0% | 7
executive thread communication design | 2 days | 0% |  | alert executive thread of low power mode
relay health information to heath thread | 3 days | 0%
GPS
python library for GPS string parsing | 5 days | 0%
update GPS values available to all threads | 1 day | 0% | 16
report health status of GPS to health thread | 3 days | 0%
Health
log hardware status messages | 2 days | 25% |  | from EPS (power) and all other hardware statuses
compose health beacon messages | 2 days | 0% | 20
initialization status after init stage | 3 days | 0% | 21
health beacon timing design | 1 days | 0% | 20
health initialization scheme | 1 days | 0%
health loop flowchart | 3 days | 0% |  | define thread global variables
zip health beacon files for globalstar thread | 2 days | 0% | 21 | send file location to globalstar thread
Executive Thread
lock management testing | 1 week | 50%
executive state machine implementation | 3 days | 25%
testing flowchart logic | 2 days | 0% | 29
testing lock management logic | 2 days | 0% | 29
low power mode logic | 1 week | 0%
Node Ejection Thread
Arduino
motor driver current monitoring | 2 days | 50%
ejection timing scheme | 3 days | 0%
I2C communication on arduino | 5 days | 0%
successful/unsuccessful response | 1 day | 0% | 37
retry on unsuccessful ejection scheme | 1 day | 0% | 38
BBB
I2C communication on BBB | 1 week | 0% |  | addressing scheme, ejection command
response identification | 1 day | 0% | 41
keep array of nodes yet to be deployed | 2 days | 25% |  | delete ejected, iterate through nodes
respond to executive thread with success | 2 days | 0%
implement initialization flowchart | 3 days | 0%
implemnet ejection loop flowchart | 5 days | 25%
report health status to health thread | 1 day | 0% | 46
RFM22B
Arduino
Uart communication with BBB | 5 days | 75%
constant listening on RFM22B radios | 3 days | 25% | 50
relay new messages to BBB | 2 days | 25% | 50
separate message into appropriate sizes | 3 days | 0% |  | check that messages fit required length
relay of messages from RFM22B thread | 2 days | 25% | 50
command recognition from BBB | 1 day | 0% | 50
new senders get added to network | 2 days | 0% | 51
retry scheme for failed messages | 3 days | 25% | 51 | recognize messages without ack response
scheme for removing nodes from network | 3 days | 0% | 57
network summary relay to BBB | 2 days | 0% | 56
initialization of new node in network | 3 days | 0% | 56 | dumy data
BBB
Uart communication with arduino
node communication telemetry list | 1 week | 25%
request for node network summary | 2 days | 0% | 59
relay data file to globalstar thread | 3 days | 0% | 62 | zip file
summary to health thread | 2 days | 0% | 64 | radio health and network summary
message type recognition | 2 days | 0% | 62 | look into contents of radio message for data, or health status - to determine routing
route messages to appropriate threads | 3 days | 0% | 62
RFM22B init flowchart implementation | 2 days | 0%
RFM22B loop flowchart implementation | 5 days | 0%
GlobalStar
test CRC computation | 2 days | 0%
separate message into appropriate sizes | 2 days | 0%
develop message packetization | 3 days | 25% | 72
file transfer/request protocol | 3 days | 25% | 74
failed CRC check protocol | 3 days | 0% | 75
failed file transmission retry | 5 days | 0% | 75
timeout on ack/nak response | 2 days | 0% | 75
find ack/nak in full read buffer | 3 days | 0% | 75
globalstart init flowchart | 5 days | 0%
globalstar loop flowchart | 1 week | 0%
empty full input buffer before read | 2 days | 0% | 81
header design for transmission | 2 days | 0%
header interpretation on message reception | 3 days | 0% | 75
routing of messages to appropriate threads | 3 days | 0% | 84
ADC
ADC init flowchart | 2 days | 0% |  | define global variables
ADC loop flowchart | 5 days | 0%
collect science data in file | 2 days | 0% | 88
route data file to globalstar thread | 3 days | 0% | 89 | ensure that this will still happen if never stops tumbling
report health status to health thread | 3 days | 0% | 88
report successful pointing/detumbling | 3 days | 0% | 88
Command Execution: Mule
Power
restart device on power line | 2 days | 0%
telemetry list of ground restart commands | 2 days | 50%
command reception from globalstar thread | 3 days | 0% | 97
low power mode override | 1 days | 0% | 98
low power mode threshold modification | 1 days | 0% | 98
exit protocol on full charge from command | 2 days | 0% | 99
GPS
message from EPS to reinitialize | 1 days | 0%
message from globalstar to edit polling rate | 1 days | 0%
Executive Thread
message reception from globalstar thread | 5 days | 0% |  | timing/interrupt scheme?
perfrom lock management for hardware reset | 3 days | 0% | 106
collect locks for low power mode entry | 4 days | 0% | 106 | alert EPS
lock collection for immediate node ejection | 5 days | 0% | 106
RFM22B
Arduino
interface to react to messages from BBB | 3 days | 0%
modify current node network vector | 3 days | 0%
perfrom dummy data test with new network | 3 days | 0%
BBB
accept network modification command | 3 days | 0%
command radio driver to | 3 days | 0%
GlobalStar
relay ground commands to repsective threads | 10 days | 0% |  | relay hardware reset to EPS, deployment override, low power mode, and deployment timing to executive thread, relay node commands to RFM22B thread, relay attitude vectors to ADC thread, relay health requests to health thread
method to store old orbit files | 2 days | 0%
manage old orbit files based on acks | 3 days | 0% | 120
re-transmit old file | 2 days | 0% | 121
modify data rate on globalstar driver | 3 days | 0%
ADC
receive commands from globalstar thread | 3 days | 0%
update attitude vectors | 5 days | 0% | 125 | check with Nick about possibility based on ADC algorithm
Day In The Life: WSN
Power
develop method of power communication |  | 0% |  | time estimate from Osi
test initial power communication | 10 days | 0% | 130
power cycle power lines | 3 days | 0% | 131
read voltage levels | 2 days | 0% | 131
read current from solar panels | 2 days | 0% | 131
develop periodic power readings | 5 days | 0% | 132
relay power reading info to health beacon | 2 days | 0% | 135
low power threshold recognition | 2 days | 0% | 135
low power mode entrance/exit protocol | 5 days | 0% | 137
Initialization
remove hardware restarts from init process | 2 days | 0%
initialize power system | 7 days | 0%
initilaze magnetometer | 2 days | 0%
input final RF specifics to radio initialization | 3 days | 0%
transmit health beacon | 4 days | 0%
Science Mode
collect magnetometer data | 3 days | 0%
add timing for 1 sec intervals | 2 days | 0%
collect temperature sensor data | 10 days | 0% |  | requires hardware selection and code development
add all new data to data file | 3 days | 0% | 148
Transfer Mode
Data file headers | 3 days | 0%
Command Execution: WSN
Power
low power mode command recognition | 3 days | 0%
low power mode exit protocol for command | 2 days | 0% | 155
Initialization
incorporate radio listens into init? | 5 days | 0%
Data Transfer Mode
command recognition | 3 days | 0%
identify hardware on power lines | 3 days | 0%
periodically listen when in transmission mode | 4 days | 0%
develop priority ranking for commands | 4 days | 0% | 160
react to commnds based on priority | 2 days | 0% | 163